## Gantt
REPORTA HEALTH MOBILE APPLICATION REBUILD
Internal Work Plan & Timeline
Project Duration: 4 Weeks (March 24, 2026 – April 21, 2026)
Team Size: 4 (2 Mobile Developers, 2 Backend Developers) ¦ Project Manager: VKM
Status: In Progress – Week 1 Complete ¦ Overall Progress: 25% ¦ On Track: Yes
Output 1b: Develop a commercial health facility discovery mobile application according to agreed specifications – Month 1
Activities | 03/24/2026 | 03/25/2026 | 03/26/2026 | 03/27/2026 | 03/28/2026 | 03/29/2026 | 03/30/2026 | 03/31/2026 | 04/01/2026 | 04/02/2026 | 04/03/2026 | 04/04/2026 | 04/05/2026 | 04/06/2026 | 04/07/2026 | 04/08/2026 | 04/09/2026 | 04/10/2026 | 04/11/2026 | 04/12/2026 | 04/13/2026 | 04/14/2026 | 04/15/2026 | 04/16/2026 | 04/17/2026 | 04/18/2026 | 04/19/2026 | 04/20/2026 | 04/21/2026
Backend Development – Week 1 (Khaleel & Oludare) – COMPLETED ✅
Mobile Development – Week 2 (Chima & Noel)
Backend Development – Week 2 (Khaleel & Oludare)
Mobile Development – Week 3 (Chima & Noel)
Backend Development – Week 3 (Khaleel & Oludare)
Mobile Development – Week 4 (Chima & Noel)
Backend Development – Week 4 (Khaleel & Oludare)