## Gantt
REPORTA HEALTH MOBILE APPLICATION REBUILD
Internal Work Plan & Timeline (Verbose Version)
Project Duration: 4 Weeks (March 24, 2026 – April 21, 2026)
Team: Khaleel, Oludare (BE) ¦ Chima, Noel (FE) ¦ PM: VKM
Status: Week 1 Complete ✅ ¦ Overall Progress: 25%
Activities | 03/24 | 03/25 | 03/26 | 03/27 | 03/28 | 03/29 | 03/30 | 03/31 | 04/01 | 04/02 | 04/03 | 04/04 | 04/05 | 04/06 | 04/07 | 04/08 | 04/09 | 04/10 | 04/11 | 04/12 | 04/13 | 04/14 | 04/15 | 04/16 | 04/17 | 04/18 | 04/19 | 04/20 | 04/21
BE W1: Foundation (Django 5, PostGIS, Docker, JWT) | bar: 03/24 to 03/25
BE W1: Core (Facility Models, Geo-Queries, Reviews) | bar: 03/26 to 03/27
BE W1: Advanced (Reports Workflow, Celery, Redis) | bar: 03/28 to 03/29
BE W1: Testing & 90-page Documentation | bar: 03/30
FE W2: RN 0.73 Init, Architecture & CI/CD | bar: 03/31
FE W2: API Layer & Auth Context Setup | bar: 04/01
FE W2: Auth Screens (Login/Signup/Forgot) | bar: 04/02
FE W2: Map Integration & Geolocation | bar: 04/03
FE W2: Facility Discovery & List Views | bar: 04/04
FE W2: Facility Details & Action Buttons | bar: 04/05
FE W2: E2E Testing & Integration | bar: 04/06
BE W2: Unit Testing (80% Coverage) & Pytest | bar: 03/31 to 04/01
BE W2: Mobile Support & Query Optimization | bar: 04/02 to 04/03
BE W2: Staging Deployment & Sentry | bar: 04/04 to 04/06
FE W3: Review System & Image Uploads | bar: 04/07
FE W3: User Profile & History Management | bar: 04/08
FE W3: Facility Reporting & Evidence Upload | bar: 04/09
FE W3: Settings, Privacy & Polish | bar: 04/10 to 04/11
FE W3: Real-device Testing & Bug Fixes | bar: 04/12 to 04/13
BE W3: Production Prep (AWS S3, SSL, SES) | bar: 04/07 to 04/09
BE W3: Load Testing & Staging Smoke Tests | bar: 04/10 to 04/11
FE W4: Final Features (Push, Deep Links) | bar: 04/14 to 04/15
FE W4: Analytics & Store Prep (Screenshots) | bar: 04/16 to 04/17
FE W4: App Store & Play Store Submission | bar: 04/18 to 04/21
BE W4: Production Deployment & CDN Setup | bar: 04/14 to 04/15
BE W4: Final Ops Handover & Runbooks | bar: 04/16 to 04/21